## Sheet1
Community Pharmacy Contractual Framework timeline.
Aspect | What needs doing | By Whom | By When | Tick when completed
CPCF | MYS application | HO | September 2019
CPCS | Declaration | HO | 29th October 2019
PQS | Aspiration Payment | HO | 1st November 2019
PQS | Declaration | HO | 14th February 2020
PQS | NHS website update | HO | 30th November 2019
PQS | Safeguarding Level 2 | All registered pharmacy professionals | 30th November 2019
PQS | CPPE Risk Management training and assessment | All registered pharmacy professionals | 30th November 2019
PQS | CPPE Sepsis online training | All registered pharmacy professionals | 30th November 2019
PQS | Virtual Outcomes Sepsis training | All pharmacy staff | 30th November 2019
PQS | Update of previous risk review | Pharmacy Manager | 31st January 2020
PQS | CPPE LASA e-learning and assessment | All registered pharmacy professionals | 30th November 2019
PQS | Annual safety report | Pharmacy Manager | 31st January 2020
PQS | Lithium audit (more information to follow) | All pharmacy staff | 1st November 2019- 31st January 2020
PQS | Sodium Valproate audit (more information to follow) | All registered pharmacy professionals | 1st November 2019- 31st January 2020
PQS | NSAID audit (more information to follow) | All pharmacy staff | Re-audit 15 patients in January 2020
PQS | Audit submission via MYS | HO | 14th February 2020
PQS | HLP level 1 self assessment | Pharmacy Manager | 4th November 2019
PQS | Dementia-friendly environment check list and action plan | HLC | 31st January 2020
PQS | Diabetes monitoring (see folder for information and tags) | All pharmacy staff | 1st October 2019 -31st January 2020. Submit numbers to Head Office by 14th February 2020
PQS | Engagement with PCN (more information to follow) | HO and PCN Lead | 14th February 2020
PQS | Asthma referral evidence | All pharmacy staff | 14th February 2020
PQS | Updated DoS | HO | 30th November 2019
PQS | SCR access | Staff eligible | 1st October 2019- 28th February 2020
kindly given to us by dean and smedley

## Sheet2
Aspect | What needs doing | By Whom | By When | Tick when completed
PQS | NHS website update | HO | 30th November 2019
PQS | Safeguarding Level 2 | All registered pharmacy professionals | 30th November 2019
PQS | CPPE Risk Management training and assessment | All registered pharmacy professionals | 30th November 2019
PQS | CPPE Sepsis online training | All registered pharmacy professionals | 30th November 2019
PQS | Virtual Outcomes Sepsis training | All pharmacy staff | 30th November 2019
PQS | Update of previous risk review | Pharmacy Manager | 31st January 2020
PQS | CPPE LASA e-learning and assessment | All registered pharmacy professionals | 30th November 2019
PQS | Annual safety report | Pharmacy Manager | 31st January 2020

## Sheet3
Aspect | What needs doing | By Whom | By When | Tick when completed
PQS | Lithium audit (more information to follow) | All pharmacy staff | 1st November 2019- 31st January 2020
PQS | Sodium Valproate audit (more information to follow) | All registered pharmacy professionals | 1st November 2019- 31st January 2020
PQS | NSAID audit (more information to follow) | All pharmacy staff | Re-audit 15 patients in January 2020
PQS | Audit submission via MYS | HO | 14th February 2020
PQS | HLP level 1 self assessment | Pharmacy Manager | 4th November 2019
PQS | Dementia-friendly environment check list and action plan | HLC | 31st January 2020
PQS | Diabetes monitoring (see pink folder for information and tags) | All pharmacy staff | 1st October 2019 -31st January 2020. Submit numbers to Head Office by 14th February 2020

## Sheet4
Aspect | What needs doing | By Whom | By When | Tick when completed
PQS | Engagement with PCN (more information to follow) | HO and PCN Lead | 14th February 2020
PQS | Asthma referral evidence | All pharmacy staff | 14th February 2020
PQS | Updated DoS | HO | 30th November 2019
PQS | SCR access | Staff eligible | 1st October 2019- 28th February 2020